## Sheet1
Phase | Estimated Time | Estimated Hours | Estimated Start Date | Estimated End Date | Charged Hours during this period
Development(Upload file) | 1 week | 40 | 2015-03-04 | 2015-03-13 | 22
Development (Reports Enhancement) | 1 week | 40 | 2015-03-16 | 2015-03-20
QA deployment and Testing | 4 days | 32 | 2015-03-23 | 2015-04-02
Production deployment and IVP confirmation | 1 day | 8 | 2015-04-03 | 2015-04-03
120
Upload file processing instructions
1. Upload file template with the CBD, UserId, Level, TLA placeholder for 12 months will be provided for the user to fill in the information
2. Once the TLA information is filled in, the file can be returned back for upload.
3. File will be loaded and validated for required information. If there is any issue, then the file with corresponding CBDs will be returned back to the user to rectify the issue.
4. Validated file will be processed for monthwise TLA. If a CBD is already available in the current cycle, it will be deactivated. New TLA for all the 12 months corresponding to the CBD will be loaded and activated. Users will see the latest TLA after the upload is completed.
5. If the variable TLA is not available for a CBD, then TLA entered on the current SPS front end will be used on the report.